Problem Statement

Intelligent Data Capture & Schedule-Linking Layer for Infrastructure Project Management: Real-Time Actual Progress Tracking (Planning-to-Execution Bridge).

HERE IS THE COMPLETE DETAIL TO DETAIL INFORMATION ABOUT THE IDEA.   Absolutely. Here is the complete BUILDO PLAZ idea specification in one place, written so you can copy and paste it directly into Replit to build the demo website.

The concept is based on your prepared SIH presentation and the workflow we developed around it. Your submitted deck describes BUILDO PLAZ as an AI-powered platform that converts supervisors' voice-based site updates into structured engineering records and links them to planned L5/L6 activities.

BUILDO PLAZ — COMPLETE WEBSITE / PRODUCT IDEA

1. Product name

BUILDO PLAZ

Tagline:

From Site Language to Project Intelligence

Alternative tagline:

Speak. Record. Track. Build.

---

2. What is BUILDO PLAZ?

BUILDO PLAZ is an AI-powered construction project assistant and progress-management platform for engineers, project managers, supervisors, and other people responsible for a construction project.

The platform creates a digital connection between:

What was planned

and

What actually happened at the construction site.

The major interaction is voice-based.

A supervisor does not have to type a complicated report. They can simply speak naturally about the day's work.

For example:

> "Today Block A footing excavation was completed. We used two machines and excavation finished around 5 PM."

The AI understands the statement, extracts useful information, converts informal/site language into standardized engineering terminology, creates a structured daily record, and suggests the corresponding planned project activity.

The engineer can then verify the AI's interpretation.

After verification, BUILDO PLAZ updates the project's actual progress and compares it with the planned schedule.

---

3. Main users

The website should support different user roles.

Project Manager

Can:

* View all projects

* View overall progress

* Monitor delays

* View project analytics

* View team activity

* Monitor risks and milestones

Engineer

Can:

* Create projects

* Add project members

* Define project activities

* Upload/import schedules

* Review supervisor updates

* Verify AI-generated records

* View planned vs actual progress

* Monitor delays and dependencies

Supervisor

Can:

* View assigned project

* View assigned activities

* Give daily voice updates

* Add photos

* Add material information

* Report completed work

* Report work started

* Report issues or delays

* View previous submissions

Optional Admin

Can:

* Manage users

* Manage projects

* Manage system settings

---

4. Main website structure

Create the website with these major sections:

Public pages

1. Landing / Home Page

2. Login

3. Register

Logged-in application

4. Main Dashboard

5. Projects

6. New Project

7. Project Overview

8. Team / Members

9. Schedule

10. AI Site Assistant

11. Daily Site Reports

12. Planned vs Actual

13. Delay & Risk

14. Materials

15. Activity Details

16. Notifications

17. Reports

18. Project History / Project Memory

19. Profile / Settings

---

5. Landing page

The landing page should immediately explain the product.

Hero section

BUILDO PLAZ

AI-powered construction execution intelligence

> Turn everyday site updates into structured engineering records, connect them to the project schedule, and track real-time progress.

Buttons:

Get Started

View Demo

Visual

Show a simple animation:

Supervisor speaks

↓

AI understands

↓

Engineering record

↓

Schedule updated

↓

Progress & delay intelligence

---

6. Login system

Users should have a simple login.

Fields:

* Email

* Password

Role can be associated with the account:

* Manager

* Engineer

* Supervisor

For the hackathon demo, you can also include:

Demo Login

with pre-created users.

Example:

Engineer Demo

[engineer@buildoplaz.demo](mailto:engineer@buildoplaz.demo)

Supervisor Demo

[supervisor@buildoplaz.demo](mailto:supervisor@buildoplaz.demo)

Manager Demo

[manager@buildoplaz.demo](mailto:manager@buildoplaz.demo)

---

7. Main dashboard

After login, users should see a dashboard appropriate to their role.

For engineer/manager:

Dashboard cards

Total Projects

Overall Progress

Activities Completed

Activities In Progress

Activities Delayed

Activities At Risk

Example

> Projects: 3

> Overall Progress: 68%

> Completed: 124

> In Progress: 31

> Delayed: 8

> At Risk: 5

---

8. New Project

The engineer or project manager clicks:

+ New Project

The form should include:

Project information

* Project Name

* Project Type

* Location

* Client

* Start Date

* Planned Completion Date

* Description

Project types:

* Building

* Bridge

* Road

* Railway

* Pipeline

* Industrial

* Water Infrastructure

* Other

This ensures BUILDO PLAZ isn't limited to bridges.

---

9. Project members

After creating the project, the engineer should add members.

Add Member

Fields:

* Name

* Email

* Phone

* Role

* Department

* Assigned Area

Roles:

Project Manager

Chief Engineer

Engineer

Supervisor

Site Engineer

Contractor

Optional:

* Civil

* Structural

* Electrical

* Mechanical

* Piping

* HSE

* Other

Each member receives access appropriate to their role.

---

10. Project overview page

When someone opens a project, show:

Project header

ABC Bridge Construction

Location: Hyderabad

Project manager: XYZ

Start: 01 Sept 2026

Planned completion: 30 June 2027

Main statistics

Overall Progress: 42%

Planned Progress: 48%

Variance: -6%

Delayed Activities: 4

At-Risk Activities: 7

---

11. Project schedule

The engineer creates or uploads the project schedule.

The schedule should contain:

* Activity ID

* Activity Name

* Description

* Discipline

* Planned Start

* Planned Finish

* Dependencies

* Assigned Team

* Status

* Progress

---

12. L1 to L6 hierarchy

BUILDO PLAZ should understand the project's hierarchical schedule.

For the prototype, explain it like this:

L1

Overall project / major milestone

L2

Major project phase

L3

Major work package

L4

Sub-work package

L5

Detailed construction activity

L6

Very granular executable task

Example:

L1: ABC Building Project

↓

L2: Foundation Works

↓

L3: Block A Foundation

↓

L4: Footing F1

↓

L5: Footing F1 Reinforcement

↓

L6: Install Bottom Reinforcement Bars for F1

The exact hierarchy can vary by project organization, so the platform should allow the project engineer to define the schedule structure.

---

13. Supervisor workspace

The supervisor should have a very simple interface.

The main screen should not look complicated.

Big buttons:

🎤 Give Voice Update

📷 Add Site Photo

📝 Add Text Update

📦 Record Materials

⚠️ Report Issue

📋 My Activities

---

14. AI Site Assistant

This is the heart of BUILDO PLAZ.

The assistant should feel like a digital project assistant.

Example greeting:

> Good morning, Rajesh. What happened at the site today?

Supervisor speaks naturally.

Example:

> "Today Block A footing excavation was completed. We started PCC in the afternoon. Two excavators were used."

The system converts speech to text.

---

15. Speech-to-Text

Pipeline:

Supervisor Voice

↓

Speech Recognition

↓

Text

Example:

> "Block A footing excavation completed today."

The system should support multiple languages where possible.

For the demo, you could support:

English + Hindi + Telugu

and demonstrate mixed/informal language.

---

16. AI language understanding

The AI should not simply transcribe.

It should understand the construction meaning.

For example:

Supervisor:

> "Block A footing ka steel kaam complete."

AI interpretation:

Activity: Footing F1 Reinforcement

Status: Completed

Location: Block A

Discipline: Civil

The objective is:

Natural/site language → Engineering terminology

This is one of the central features of your concept.

---

17. Structured information extraction

From every voice update, AI should extract fields such as:

Activity

What work was performed?

Location

Where was it performed?

Status

Started / In Progress / Completed / Delayed

Date

When did it occur?

Start time

When did the activity start?

End time

When did the activity finish?

Quantity

How much work was completed?

Unit

m³ / m² / tonnes / metres / units / etc.

Materials

What materials were used?

Equipment

What equipment was used?

Workforce

How many workers were involved?

Issues

What problems occurred?

Remarks

Additional information.

---

18. Automatic engineering record

After the supervisor speaks, display the extracted information.

Example:

AI GENERATED SITE RECORD

Date: 16 Sept 2026

Location: Block A

Activity: Footing F1 Reinforcement

Status: Completed

Quantity: 1 footing

Materials: Reinforcement steel

Actual End: 5:20 PM

Source: Supervisor Voice

AI Confidence: 94%

Then show:

Suggested Schedule Match

CIV-FND-006 — Footing F1 Reinforcement

Confidence: 94%

Buttons:

✓ Approve Match

✎ Edit

---

19. Human verification

Do not let AI automatically make every official change.

The engineer should see:

> AI detected this activity

and verify it.

This gives the platform a human-in-the-loop workflow.

Buttons:

Approve

Edit

Reject

After approval, the official progress record is updated.

---

20. L5/L6 activity matching

Suppose the project schedule contains:

CIV-006 — Footing F1 Reinforcement

Supervisor says:

> "F1 footing steel work finished."

The AI identifies the semantic relationship.

It should show:

Possible Match

CIV-006 — Footing F1 Reinforcement

94% confidence

The system shouldn't depend on exact wording.

Different people can describe the same activity differently.

---

21. Multiple supervisors

This is very important to your concept.

A large project can have many supervisors.

For example:

Supervisor A

Foundation area

Supervisor B

Structural works

Supervisor C

Road works

Supervisor D

Electrical works

Each person submits updates separately.

BUILDO PLAZ combines those updates into one project-level view.

So:

Supervisor A

↓

Foundation Update

Supervisor B

↓

Structural Update

Supervisor C

↓

Road Update

All go into:

CENTRAL PROJECT EXECUTION RECORD

This eliminates fragmented reporting across different site areas.

---

22. Daily site report

Create a page called:

Daily Site Report

Example:

Project: ABC Bridge

Date: 16 Sept 2026

Civil

Foundation excavation — Completed

Pile reinforcement — 80%

Pier reinforcement — Started

Materials

Steel — 12 tonnes received

Concrete — 18 m³ used

Equipment

Excavator — 2

Concrete mixer — 1

Workforce

Workers — 42

Issues

Material delivery delayed by 4 hours

AI Summary

> Foundation excavation completed. Pier reinforcement started. Steel delivery received. Concrete placement completed for designated footing.

---

23. Planned vs Actual dashboard

This should be one of the most impressive parts of the demo.

Show two values:

Planned

48%

Actual

42%

Variance: -6%

Then show a timeline.

Example:

| Activity      | Planned | Actual  | Status   |

| ------------- | ------- | ------- | -------- |

| Excavation    | 12 Sept | 14 Sept | Delayed  |

| PCC           | 14 Sept | 15 Sept | Delayed  |

| Reinforcement | 17 Sept | 17 Sept | On Track |

Use visual indicators:

🟢 On Track

🟡 At Risk

🔴 Delayed

---

24. Delay detection

When the actual date differs from the planned date:

Example:

Planned finish: 12 Sept

Actual finish: 15 Sept

System:

> 3-day delay detected

Then identify possible downstream impacts.

---

25. Dependency impact

Suppose:

Excavation

↓

PCC

↓

Reinforcement

↓

Formwork

↓

Concrete

If excavation is delayed, display:

⚠️ Downstream Impact

PCC: At Risk

Reinforcement: At Risk

Formwork: Monitoring

The system should visualize this using a dependency graph.

---

26. Delay reasons

Allow the AI to categorize reasons from supervisor updates.

Examples:

* Material shortage

* Equipment failure

* Labour shortage

* Weather

* Design change

* Approval delay

* Site access

* Safety issue

* Contractor issue

* Other

Then the manager can see recurring causes.

---

27. Materials management

Create:

Materials

The supervisor can say:

> "Today 12 tonnes of reinforcement steel arrived."

AI extracts:

Material: Reinforcement Steel

Quantity: 12

Unit: tonnes

Date: 16 Sept

Location: Block A

Status: Received

The engineer/manager can see:

Material Received

Material Used

Material Remaining

---

28. Site photos

Supervisor can upload photographs.

For the demo:

Add Site Photo

The system stores:

* Project

* Location

* Date

* Supervisor

* Related activity

Optional AI capability:

Photo → suggested activity

Example:

> Possible activity: Column reinforcement

with a confidence score.

Keep this as an optional demo feature rather than making it essential.

---

29. Project progress page

Show:

Overall Project

42%

Civil

55%

Structural

37%

Electrical

21%

Mechanical

30%

Also show activity status:

Completed

In Progress

At Risk

Delayed

---

30. Manager dashboard

The manager needs a high-level view.

Show:

Project Health

Overall: At Risk

Schedule

-6% variance

Open Issues

12

Delayed Activities

8

Materials

3 critical items

Recent Updates

Latest supervisor submissions.

---

31. Engineer dashboard

Engineer should see more technical detail.

Show:

* Pending AI matches

* L5/L6 activities

* Planned vs actual

* Site reports

* Activity history

* Delay analysis

* Material updates

* Team updates

* Verification queue

---

32. Supervisor dashboard

Keep it simple.

Show:

Today's Activities

Give Update

My Reports

Materials

Issues

Notifications

Avoid complicated charts for supervisors.

---

33. Notifications

Examples:

> 🔴 Activity delayed by 2 days.

> 🟠 PCC activity is at risk due to excavation delay.

> 🔵 New supervisor report awaiting verification.

> 🟢 Activity CIV-006 completed.

> ⚠️ Material shortage reported.

---

34. Project history

Every update should remain available.

For example:

16 Sept

Supervisor A:

Foundation excavation completed.

15 Sept

Supervisor B:

PCC started.

14 Sept

Material delivery delayed.

The project becomes a digital execution history.

---

35. Project memory / intelligence

Over time, BUILDO PLAZ can analyze historical data.

Example:

Historical Insight

> Foundation reinforcement activities on similar projects averaged 4.2 days against planned 3 days.

Common delay reason

> Material availability

Frequently delayed activity

> Foundation reinforcement

This turns the platform from a reporting tool into an execution intelligence system.

For your MVP, this can be simulated with sample historical data.

---

36. Search

Provide global project search.

Engineer can search:

> "Footing F1"

and see:

* planned activity

* actual records

* supervisor updates

* photos

* materials

* delays

* history

---

37. Reports

Allow users to generate:

Daily Report

Weekly Progress Report

Monthly Project Report

Delay Report

Material Report

Activity Report

Supervisor Activity Report

For the demo, a simple PDF/download button can be shown even if the actual export is mocked initially.

---

38. Recommended database structure

For Replit, structure the backend around entities such as:

Users

* id

* name

* email

* role

* department

Projects

* id

* name

* type

* location

* start_date

* planned_end_date

* manager_id

ProjectMembers

* project_id

* user_id

* role

Activities

* id

* project_id

* parent_activity_id

* level

* activity_code

* activity_name

* discipline

* planned_start

* planned_finish

* actual_start

* actual_finish

* status

* progress

SiteUpdates

* id

* project_id

* user_id

* audio

* transcript

* created_at

AIRecords

* id

* site_update_id

* activity_id

* extracted_data

* engineering_interpretation

* confidence

* verification_status

Materials

* id

* project_id

* material_name

* quantity

* unit

* received_or_used

* date

Issues

* id

* project_id

* activity_id

* category

* description

* severity

* status

Notifications

* id

* user_id

* type

* message

* read

ProjectHistory

* id

* project_id

* activity_id

* event_type

* old_value

* new_value

* timestamp

* user_id

---

39. Recommended technical stack

Your current PPT specifies:

Frontend: HTML, CSS, JavaScript / React

AI/NLP: Speech-to-Text, LLM, Engineering Terminology Extraction

Backend: Python + FastAPI

Database: PostgreSQL.

For a Replit MVP, a practical implementation can therefore be:

Frontend

React

Styling

CSS / Tailwind

Backend

FastAPI / Python

Database

PostgreSQL

AI layer

Speech-to-text + LLM

Authentication

Session/JWT-based authentication

Charts

Chart library for progress and schedule visualization

---

40. AI architecture

The AI pipeline should look like:

Voice Input

↓

Speech-to-Text

↓

Language Detection

↓

Construction Context Understanding

↓

Entity / Activity Extraction

↓

Engineering Terminology Normalization

↓

L5/L6 Semantic Matching

↓

Confidence Score

↓

Engineer Verification

↓

Database

↓

Progress Engine

↓

Delay / Dependency Engine

↓

Dashboard

---

41. Example complete interaction

Supervisor

🎤

> "Today Block A footing ka steel ka kaam complete ho gaya. Twelve tonnes steel received and concrete work will start tomorrow."

AI

Detected information

Activity:

Footing F1 Reinforcement

Status:

Completed

Material:

Reinforcement Steel

Quantity:

12 tonnes

Next activity:

Footing Concrete

Suggested schedule activity:

CIV-FND-006

Confidence:

95%

Engineer

Clicks:

Approve

System

Updates:

CIV-FND-006 → 100%

Then:

Planned finish: 15 Sept

Actual finish: 16 Sept

Variance: +1 day

Next activity:

Footing Concrete → At Risk

---

42. The main dashboard experience

The final website should feel like this:

```text

BUILDO PLAZ

────────────────────────────────────

Good Morning, Engineer

Projects                         3

Overall Progress                68%

Delayed Activities               8

At-Risk Activities               5

Pending Verifications            4

────────────────────────────────────

PROJECTS

ABC Bridge Project              68%

ABC Building Project             42%

Pipeline Project                 76%

────────────────────────────────────

RECENT SITE UPDATES

🎤 Supervisor Ravi

Foundation excavation completed

10 min ago

🎤 Supervisor Arun

Steel delivery received — 12 tonnes

25 min ago

⚠️ Delay detected

PCC activity is at risk

40 min ago

────────────────────────────────────

PLANNED       ACTUAL

72%           68%

Schedule Variance: -4%

────────────────────────────────────

```

---

43. The most important demo

Do not try to demonstrate every feature during the hackathon.

Your main demo should be:

STEP 1

Engineer creates:

ABC Building Project

STEP 2

Engineer adds:

Manager + Engineer + 3 Supervisors

STEP 3

Engineer creates/imports schedule.

STEP 4

Supervisor opens:

AI Site Assistant

STEP 5

Supervisor speaks:

> "Today Block A footing excavation completed."

STEP 6

AI shows:

Transcription

↓

Engineering interpretation

↓

L5/L6 activity match

↓

Confidence

STEP 7

Engineer clicks:

Approve

STEP 8

Dashboard immediately changes:

Actual Progress ↑

STEP 9

Show:

Planned vs Actual

STEP 10

Create a delay scenario.

Show:

Activity delayed → downstream activity at risk

That is the core BUILDO PLAZ story.

---

44. What BUILDO PLAZ is NOT

This is important when explaining the product.

It is not simply:

❌ A construction diary

❌ A voice transcription app

❌ A project dashboard

❌ A generic chatbot

❌ A translation tool

Its main purpose is the connection:

> Site communication → structured engineering information → schedule activity → actual progress → project intelligence

HIGHLIGHT THE L5 AND L6 ACTIVITIES.

Simple example: Building a foundation

L1 – Project

Construction of ABC Building

L2 – Major phase

Foundation Works

L3 – Work package

Block A Foundation

L4 – Sub-package

Footing F1

L5 – Detailed activity

Footing F1 Reinforcement

L6 – Very specific executable task

Install bottom reinforcement bars for Footing F1

So:

L5 = detailed construction activity

L6 = even more specific task/activity under it

45. One-sentence definition

> BUILDO PLAZ is an AI-powered project assistant that transforms supervisors' natural voice-based site updates into structured engineering records, maps them to detailed L5/L6 activities, and provides engineers and managers with real-time project progress and delay intelligence.

46. One-minute explanation

>BUILDO PLAZ is a digital AI assistant for construction teams. Engineers and project managers create a project and define its detailed schedule, while multiple supervisors can report their daily work simply by speaking instead of filling complex manual reports. The AI understands the supervisor's natural or local language, converts it into standard engineering terminology, extracts details such as activity, quantity, materials and timing, and matches the update to the correct L5/L6 activity in the project schedule. The engineer verifies the AI's suggestion, after which BUILDO PLAZ updates actual progress, compares it with planned progress, and identifies delays and downstream schedule risks. All supervisors' updates come together into one centralized project view for engineers and managers.